# Round 1: Minute-by-Minute Flow

28 September 2026

## Overview

Round 1 runs 40 teams across four rooms. Chits are hidden in two seminar halls, one per slot.

| Item | Details |
| --- | --- |
| Teams | 40 |
| Competition rooms | 402, 403, 404, 405 |
| Chit locations | Seminar Hall 306 (1st slot), Seminar Hall 406 (2nd slot) |

## APC member allocation

| Assignment | Members | Role |
| --- | --- | --- |
| Dynamic POC | 2 | Floating points of contact across venues |
| Seminar Hall 306 / 406 | 2 | Manage the chit locations |
| Room 402 / 403 | 3 per room | 2 on the scoresheet, 1 emcee |

## Timeline

The round is 30 minutes of solving plus a 20-minute buffer, after 15 minutes of instructions.

- Instructions and settlement (15 min): teams take their seats and are briefed on the rules.

- Solving block 1 (15 min): the round starts and both members work in parallel.

- Solving block 2 (15 min): solving continues.

- Buffer (20 min): submissions by mail or Google Form, plus chit checking.

Open question: the whiteboard reads “Total Duration: 30 mins + 20 mins buffer” with two 15-minute solve blocks. Confirm whether the 15-minute instructions count toward the 30 minutes.

## Team member roles during the round

Each team’s two members split up when solving starts.

| Member | Task |
| --- | --- |
| Member 1 | Solves the Excel problem |
| Member 2 | Finds the chits and solves them, then writes the final answer on the back of the chit |

## Post-round buffer

- Collect team submissions by mail and Google Form

- Check the chits Member 2 handed in

- Record results on the scoresheets in rooms 402 and 403